| SUKHAM100 Sankalp se Rachnatmak Jeevan Tak | MONTH 01 PROGRAMME IMPLEMENTATION PLAN |
| --- | --- |

MY HEALTH, MY PRIDE

Weeks 1–4  •  20 September – 16 October 2026

| WEEK / DATES | PROGRAMME & SCOPE | HOW TO ORGANISE | WHO CAN PARTICIPATE |
| --- | --- | --- | --- |
| Week 1 20–26 Sep 2026 | Rashtriya Sankalp Samaroh (Health and Nasha Mukt Pledge + Signature Campaign) SCOPE Begin with a collective commitment to healthy, addiction-free living and connect healthy choices with personal responsibility. | - Arrange venue, banner, pledge text, signature sheets and attendance. - Give a brief health and Nasha Mukt message; include a short Rajyoga/meditation experience where suitable. - Conduct the pledge and signature campaign. - Optional: slogan writing, poster-making, street play or group discussion. • Obtain permissions for public activities. | Families, community members, educational institutions, health and social organisations, MY Bharat volunteers and partner organisations. |

| WEEK / DATES | PROGRAMME & SCOPE | HOW TO ORGANISE | WHO CAN PARTICIPATE |
| --- | --- | --- | --- |
| Week 2 27 Sep–3 Oct 2026 | Health Check-up & BMI Camp + Meditation Camp SCOPE Promote preventive health awareness through basic assessment, individual guidance and meditation/wellness. | - Coordinate with a local health institution and qualified professionals. - Confirm available checks, equipment, privacy, consent and referral arrangements. - Register participants; conduct only the checks agreed with professionals. - Provide results privately and refer concerns appropriately. - Add a guided meditation/Rajyoga and healthy-lifestyle session. | Families and community members; local doctors, health professionals, colleges and health institutions as partners. |

CONTINUED ON PAGE 2  →

| SUKHAM100 Sankalp se Rachnatmak Jeevan Tak | MONTH 01 PROGRAMME IMPLEMENTATION PLAN |
| --- | --- |

MY HEALTH, MY PRIDE

Weeks 1–4  •  20 September – 16 October 2026

| WEEK / DATES | PROGRAMME & SCOPE | HOW TO ORGANISE | WHO CAN PARTICIPATE |
| --- | --- | --- | --- |
| Week 3 4 Oct–10 Oct 2026 | Health Walk/Run SCOPE Encourage physical activity and visible community participation through a 3–5 km walk/run, adapted to local conditions. | - Select and inspect a safe route; obtain required permissions. - Arrange registration, route marshals, hydration, first aid and an emergency contact plan. - Brief participants and conduct a suitable warm-up. - Conduct the walk/run; offer a walking option and avoid pressure to run. - Close with a health/Nasha Mukt message and practical commitment. | Community members, walkers/runners, families, BK Centres, educational institutions, MY Bharat volunteers and partner organisations. |

| WEEK / DATES | PROGRAMME & SCOPE | HOW TO ORGANISE | WHO CAN PARTICIPATE |
| --- | --- | --- | --- |
| Week 4 11–16 Oct 2026 | University Health & Well-being Mela SCOPE Bring institutions and community partners together for health awareness, interaction and cultural/creative activities. | - Partner with a college/university and agree on roles, venue and schedule. - Plan interactive awareness stations, cultural activities and a meditation/wellness experience. - Assign stage, venue, safety and documentation responsibilities. - Invite participants to share practical healthy-living commitments. - Agree on any follow-up collaboration. | Colleges and universities, faculty, families, BK Centres, community members, MY Bharat volunteers and partner organisations. |

| REPORTING Record date, venue, activity, participant totals/categories, facilitators/partners, outcomes and 2–5 permitted photographs. Submit through the existing SUKHAM100 reporting workflow at https://services.bkmedicalwing.org/sukham100-activity-entry/ | SAFETY & INCLUSION Use qualified professionals for health checks; protect personal health information; obtain required permissions and consent; adapt physical activities to local conditions. |
| --- | --- |